## Checklist
Project Title: |  |  |  | Date:
WIN:
Route: |  |  |  | PIN:
MP(s): |  |  |  | List any additional PINs at bottom or attached to this form.
Cost:
Part I ― Cost | [8 empty] | RCW 47.20.785 does not encourage Design-Build for a project contract cost (PE & Construction) less than $2 Million
Is the Project Estimate less than $2 Million?
☐ Yes ― A selection process and authorization are not required ― the delivery method is Design-Bid-Build.
☐ No ― Continue to Part II
Part I ― RCW 47.20.785 Project Qualifications for Design-Build Method
1. | Are construction activities highly specialized? |  |  |  |  | ☐ | Yes | ☐ | No
2. | Are there complex staging, maintenance of traffic, constraints, risks, etc. that will affect the construction methodology? |  |  |  |  | ☐ | Yes | ☐ | No
3. | Does the project provide opportunity for greater innovation & efficiencies between the designer & builder? |  |  |  |  | ☐ | Yes | ☐ | No
4. | Would use of DB result in significant reduction to the overall project schedule or critical milestones? |  |  |  |  | ☐ | Yes | ☐ | No
If Yes was selected for any of questions 1 through 4 above, Design-Build is a viable PDM option. (Go to Part II)
If No was selected for all of the questions 1 through 4 above, it indicates Design-Bid-Build as the PDM ― get Authoriztion Level listed at end of form.
Part II ― Project Questions
S C H E D U L E | A. | Are there 3rd party agreements with local government or agencies that require a full design before execution? (Is a significant portion of the project impacted?) |  |  |  | ☐ | Yes | ☐ | No
Justification:
| B. | Are there long lead, lengthy environmental permits or ROW issues that would delay start of Construction? (Is a significant portion of the project impacted?) |  |  |  | ☐ | Yes | ☐ | No
Justification:
| C. | Is early obligation of funds necessary? (Such as a deadline to obligate grant funding) |  |  |  | ☐ | No | ☐ | Yes
Justification:
| D. | Is there time to prepare 100% design? |  |  |  | ☐ | Yes | ☐ | No
Justification:
| E. | Is there a need to compress the schedule? |  |  |  | ☐ | No | ☐ | Yes
Justification:
| F. | Do funding limits restrict when the schedule can start? (Such as the Biennium) |  |  |  | ☐ | Yes | ☐ | No
Justification:
C O M P L E X I T Y & I N N O V A T I O N | G. | Are there significant risks that could be better managed by others than WSDOT? |  |  |  | ☐ | No | ☐ | Yes
Justification:
| H. | Does the project involve specialty engineering or high-tech designs or have other opportunities for innovation? |  |  |  | ☐ | No | ☐ | Yes
Justification:
| I. | Does the project require complex phasing and staging with the possibility of high impacts to the public? |  |  |  | ☐ | No | ☐ | Yes
Justification:
| J. | Does an existing road or facility need to remain in service? (no options for detour, or no alternate facility available, and a significant portion of the project is impacted) |  |  |  | ☐ | No | ☐ | Yes
Justification:
| K. | Is WSDOT willing to give up control of design and/or construction on this project? |  |  |  | ☐ | No | ☐ | Yes
Justification:
| L. | Are critical 3rd party involvement and changes likely during design & construction? |  |  |  | ☐ | Yes | ☐ | No
Justification:
COST | M. | Is early certainty of the total project cost important? (Increased certainty of total cost early in the project needed due to funding or project constraints) |  |  |  | ☐ | No | ☐ | Yes
Justification:
Sum each column to the right―a checked answer is worth one (1) point. The column with the most points indicates the recommended delivery method. | [5 empty] | DBB |  | DB
Project Delivery Method indicated from the responses to the questions in Part III (above) |  |  |  |  | Score: | 0 |  | 0
☐ DBB ☐ DB ☐ Inconclusive
The project cost is:
☐ | less than $25 million ― get Authorization Level 1 (below)
☐ | $25 million or greater, but less than $100 million ― get Authorization Levels 1 & 2 (below)
☐ | $100 million or greater ― Workshop to get Authorization Levels 1 & 2 (below)
Final Project Delivery Method Selected
☐ Design-Bid-Build ☐ Design-Build
Authorization Level 1
Project Engineer
Name: |  |  | Signature: | [5 empty] | ______________________________________________
PDE/EM Manager
Name: |  |  | Signature: | [5 empty] | ______________________________________________
Authorization Level 2
Regional Administrator
Name: |  |  | Signature: | [5 empty] | ______________________________________________
Attach project information, assumptions and additional justification to Form